Prevention North

Region1 WV Substance Abuse Prevention Services Sub-Grantee Statement of Work 2022-2023

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Community-Based Process Level of Effort: 25% | Identify 1 Coordinator of WV Prevention Services in Each County | 11/30/2022 |  |
|  | Submit 2023 Comprehensive County Substance Abuse Prevention Plan To Include: Statement of Need Population of Focus Organizational Experience (Staff and Volunteers) Community Needs Assessment Logic Model Action Plan Data Collection and Performance Measurement Sustainability | 12/30/2022 |  |
|  | Participate in Coalition Capacity-Building Training & TA | 09/30/2023 |  |
|  | Facilitate a Minimum of 1 Community Coalition Meeting/Event Each Month | 09/30/2023 |  |
|  | Attend Region1 WVSAPS Sub-Grantee Meetings Quarterly | 09/30/2023 |  |
|  | Attend Region1 Data & Planning Team Meetings Quarterly | 09/30/2023 |  |
|  | Attend Region1 Women’s Network Meetings | 09/30/2023 |  |
|  | Attend Any BBH or Office of Drug Control Policy Meetings in Region1 | 09/30/2023 |  |
|  | Complete Annual CADCA Coalition Survey | 09/30/2023 |  |
|  | Collection of Attendance Demographic Data & Participant Feedback | 09/30/2023 |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Education Level of Effort: 25% | Coordinate the Implementation for a Minimum of 1 Evidence-Based Prevention Education Curriculum in Each County | 05/31/2023 |  |
|  | Coordinate a Minimum of 2 Strategic Prevention Framework (SPF) Trainings in Each County | 09/30/2023 |  |
|  | Coordinate a Minimum of 2 “The Prevention Guide What Works and What Doesn’t” Trainings in Each County | 09/30/2023 |  |
|  | Coordinate a Minimum of 2 Substance Abuse Prevention Skills Training (SAPST) in Each County | 09/30/2023 |  |
|  | Coordinate a Minimum of 2 Addressing Stigma Trainings in Each County | 09/30/2023 |  |
|  | Complete National CADCA Coalition Academy | 09/30/2023 |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Environmental Level of Effort: 20% | Promote Region1 Rx Drug Drop Boxes & Participate in Rx Take-Back Events in County | 04/30/2023 |  |
|  | Distribute Deterra Prescription Drug Disposal Bags in County | 04/30/2023 |  |
|  | Coordinate & Implement Synar Compliance Inspections in County | 08/31/2023 |  |
|  | Identify and Implement a Minimum of 1 Environmental Strategy Based on Community Needs Assessments in Each County | 09/30/2023 |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Alternatives Level of Effort: 15% | Establish and Maintain a Minimum of 1 Youth Coalition in Each County Ex. Youth MOVE | 09/30/2023 |  |
|  | Identify and Coordinate a Minimum of 1 Positive Youth Alternative Activity in Each County | 09/30/2023 |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| Information Dissemination Level of Effort: 10% | Coordinate Region1 Positive Community Norms Media Campaign Development & Implement in Each County | National Prevention Wk |  |
|  | Promote Prevention 1st, Help 4 WV, Help & Hope WV and Stigma Free WV, Children’s Crisis and Referral line, Naloxone, and Mental Health First Aid Training, and the 988 Suicide and Crisis Lifeline at Community Meetings & a Minimum of 1 Community-Based Event | 09/30/2023 |  |
|  | Promote participation by Schools in the West Virginia School Learning Environmental Survey | 09/30/2023 |  |

| Strategy | Deliverable | Target Date |  |
| --- | --- | --- | --- |
| ID & Referral Level of Effort: 5% | Facilitate Referral to Services in Each County | 09/30/2023 |  |

Submit County Activity Reporting Forms (to Include Associated Costs) And Financial Reporting Forms No Later Than the 5th Work Day of the Following Month